## 📋 Release Overview
ZUPHARM LABORATORIES — MANUFACTURING PAGE
Release Notes ¦ Version 1.0.0 ¦ 30 May 2026
# | Section | Component / Feature | Description | Type | Status | Priority
1 | Hero Banner | Page Header | State of the Art Manufacturing — teal hero with WHO-GMP tagline | New Feature | ✅ Live | High
2 | Hero Banner | Announcement Strip | PCD Franchise banner for Bihar, UP & Jharkhand with Apply Today CTA button | New Feature | ✅ Live | High
3 | Navigation | Active Tab Highlight | Manufacturing tab highlighted teal in navbar across all scroll positions | Enhancement | ✅ Live | Medium
4 | Tab Section | Sterile Injectables Tab | ISO Class 5/Grade A cleanrooms, Lyophilization lines, 50M+ vials/ampoules capacity | New Feature | ✅ Live | High
5 | Tab Section | Oral Solid Dosage Tab | Tablet, capsule, blister packaging info with product image | New Feature | ✅ Live | High
6 | Tab Section | Advanced R&D Tab | ICH stability chambers, HPLC suite, tech transfer support | New Feature | ✅ Live | High
7 | FAQ Accordion | Regulatory Certifications | WHO-GMP, ISO 9001:2015, FSSAI, CDSCO / Schedule M expandable answer | New Feature | ✅ Live | High
8 | FAQ Accordion | Contract Manufacturing | End-to-end CMO services info in expandable FAQ item | New Feature | ✅ Live | Medium
9 | FAQ Accordion | Production Lead Time | 30–45 days lead time info with urgent slot note | New Feature | ✅ Live | Medium
10 | Quality Section | Clinical Research | Bioequivalence & clinical research accordion item | New Feature | ✅ Live | Medium
11 | Quality Section | QA & Validation | ISO 9001:2015, zero-defect manufacturing principles accordion | New Feature | ✅ Live | High
12 | Quality Section | Innovation & Product Dev | Product development pipeline info accordion item | New Feature | ✅ Live | Medium
13 | Brochure Download | PDF CTA Block | Manufacturing Capability Brochure — 4.2 MB PDF download button | New Feature | ⚠️ Pending | High
14 | Footer | Navigation Links | Home, About, Products, PCD Franchise, Manufacturing & Certifications, Contact | New Feature | ✅ Live | Medium
15 | Footer | Product Categories | Cardiac Care, Neurology, Respiratory, Paediatrics, Anti-infectives, Diabetology, Opthal. | New Feature | ✅ Live | Medium
16 | Footer | Contact Block | Address (Patna), phone, email, website — placeholder values to be updated | New Feature | ⚠️ Pending | High

## 🚀 Deployment Activities (hidden)
DEPLOYMENT ACTIVITY LIST — Manufacturing Page v1.0.0
Environment: Localhost → Hostinger (Production) ¦ Target Date: 30 May 2026
# | Phase | Activity | What to Do | How to Do It | Owner | Status | Notes
1 | PRE-DEPLOYMENT | Code Review | Review all Manufacturing page components | Check all JSX/TSX files, validate props, remove console.logs | Dev | ⬜ Pending
2 | PRE-DEPLOYMENT | Content Verification | Verify all text content is approved by client | Cross-check copy with client-approved document; check spelling | Dev + PM | ⬜ Pending | Especially FAQ answers
3 | PRE-DEPLOYMENT | Replace Placeholder Data | Update contact info in Footer | Replace +91 12345 67890 and info@zupharm.com with actual client details | Dev | ⬜ Pending | CRITICAL before go-live
4 | PRE-DEPLOYMENT | Image Audit | Replace stock photos with real facility images | Get actual plant/lab images from client; compress to <200KB each | Dev + Client | ⬜ Pending | Sterile Inj. & R&D tabs
5 | PRE-DEPLOYMENT | PDF Brochure | Link actual brochure PDF | Get final PDF from client, upload to /assets/, update download href | Dev | ⬜ Pending | Currently linked to PNG placeholder
6 | PRE-DEPLOYMENT | Responsive Testing | Test on mobile, tablet, desktop | Use Chrome DevTools — test at 375px, 768px, 1280px, 1920px breakpoints | Dev | ⬜ Pending
7 | PRE-DEPLOYMENT | Cross-Browser Testing | Test on Chrome, Firefox, Edge | Open site in each browser, check tab switching, accordion, CTA buttons | Dev | ⬜ Pending
8 | PRE-DEPLOYMENT | Performance Audit | Run Lighthouse audit | Chrome DevTools → Lighthouse → run for Performance, SEO, Accessibility | Dev | ⬜ Pending | Target score ≥ 85
9 | BUILD | Production Build | Run npm build command | Terminal: npm run build — verify no errors or warnings in output | Dev | ⬜ Pending
10 | BUILD | Build Verification | Test the production build locally | Run: npm run preview — check /manufacturing route works correctly | Dev | ⬜ Pending
11 | BUILD | Asset Check | Verify all assets are bundled | Check /dist folder — confirm images, fonts, CSS all present | Dev | ⬜ Pending
12 | BUILD | Environment Variables | Set production env variables | Create .env.production with correct API keys / base URLs if any | Dev | ⬜ Pending
13 | DEPLOYMENT | Hostinger Login | Login to Hostinger hPanel | Go to hpanel.hostinger.com → login with client credentials | Dev | ⬜ Pending
14 | DEPLOYMENT | File Upload | Upload /dist build files to server | hPanel → File Manager → public_html → upload all files from /dist | Dev | ⬜ Pending | Or use FTP via FileZilla
15 | DEPLOYMENT | Subdomain Config | Point subdomain to correct folder | hPanel → Domains → Subdomains → set document root to correct /dist path | Dev | ⬜ Pending | Under Natural Elements domain
16 | DEPLOYMENT | SSL Certificate | Enable HTTPS on subdomain | hPanel → SSL → enable Let's Encrypt for subdomain, wait for propagation | Dev | ⬜ Pending
17 | POST-DEPLOYMENT | Smoke Testing | Verify all page sections load correctly | Open live URL → check hero, tabs, FAQ, quality section, footer, brochure download | Dev | ⬜ Pending
18 | POST-DEPLOYMENT | 404 Check | Check no broken links | Click every nav link, CTA button, footer link — verify no 404s | Dev | ⬜ Pending
19 | POST-DEPLOYMENT | Client UAT | Client does User Acceptance Testing | Share live URL with client, get written approval sign-off | PM | ⬜ Pending | Required before final handover
20 | POST-DEPLOYMENT | Go-Live Confirmation | Send deployment confirmation email | Email client with live URL, login details, brochure upload instructions | PM | ⬜ Pending

## 🔧 Build Manifest (hidden)
BUILD MANIFEST — Zupharm Manufacturing Page v1.0.0
Build Date: 30 May 2026 ¦ Environment: Production ¦ Framework: React + Vite
A. BUILD INFORMATION
Project Name |  | Zupharm Laboratories Website
Module |  | Manufacturing Page (/manufacturing)
Version |  | v1.0.0
Build Tool |  | Vite
Framework |  | React
Node Version |  | v18.x or above
Package Manager |  | npm
Build Command |  | npm run build
Output Directory |  | /dist
Preview Command |  | npm run preview
Deploy Target |  | Hostinger (Subdomain under Natural Elements)
Routing |  | React Router DOM — /manufacturing route
B. FILES CHANGED / CREATED
# | File Path | File Type | Change Type | Description | Status
1 | src/pages/Manufacturing.jsx | JSX Component | Created | Main Manufacturing page component with all sections | ✅ Done
2 | src/components/ManufacturingHero.jsx | JSX Component | Created | Hero banner section with teal background and CTA | ✅ Done
3 | src/components/CapabilityTabs.jsx | JSX Component | Created | 3-tab section: Sterile, Oral Solid, Advanced R&D | ✅ Done
4 | src/components/FAQAccordion.jsx | JSX Component | Created | Expandable FAQ section under Audits & Standards | ✅ Done
5 | src/components/QualitySection.jsx | JSX Component | Created | Research & Quality accordion with 3 items | ✅ Done
6 | src/components/BrochureDownload.jsx | JSX Component | Created | PDF brochure CTA block with download button | ⚠️ PDF Pending
7 | src/App.jsx | JSX Component | Modified | Added /manufacturing route to React Router config | ✅ Done
8 | src/components/Navbar.jsx | JSX Component | Modified | Active state added for Manufacturing nav link | ✅ Done
9 | src/components/Footer.jsx | JSX Component | Modified | Added Manufacturing & Certifications to footer nav links | ⚠️ Content Pending
10 | public/assets/manufacturing/ | Image Assets | Created | Folder for manufacturing page images (tabs) | ⚠️ Stock images
11 | public/brochure/manufacturing.pdf | PDF Asset | Pending | Client brochure file — to be provided by client | ⬜ Pending
12 | src/styles/manufacturing.css | CSS File | Created | Page-specific styles, tab active states, accordion anim | ✅ Done
C. KEY DEPENDENCIES
# | Package | Version | Purpose | Type
1 | react | ^18.x | Core UI framework | dependency
2 | react-dom | ^18.x | DOM rendering | dependency
3 | react-router-dom | ^6.x | Client-side routing (/manufacturing) | dependency
4 | vite | ^5.x | Build tool & dev server | devDependency
5 | tailwindcss | ^3.x | Utility CSS (if used) | devDependency

## ⚠️ Issues & Sign-off (hidden)
KNOWN ISSUES & SIGN-OFF — Manufacturing Page v1.0.0
KNOWN ISSUES
# | Issue | Section Affected | Severity | Action Required | ETA
1 | Brochure download links to placeholder PNG, not actual PDF | Brochure Download Block | HIGH | Client to provide PDF; Dev to update href | Before Go-Live
2 | Footer contact details are placeholder values | Footer | HIGH | Replace with verified client phone/email/address | Before Go-Live
3 | Tab images are stock photos, not real facility images | Capability Tabs | MEDIUM | Client to provide actual plant/lab photographs | Post-Launch v1.1
4 | FAQ answers partially truncated on small screen widths | FAQ Accordion | LOW | Adjust accordion min-height for mobile viewport | Post-Launch v1.1
5 | No analytics tracking on CTA buttons | Apply for Franchise / CTAs | LOW | Integrate Google Analytics event tracking | Post-Launch v1.1
SIGN-OFF & APPROVALS
Role | Name | Signature / Initials | Date | Status
Developer |  |  | 30 May 2026 | ⬜ Pending
Project Manager |  |  | 30 May 2026 | ⬜ Pending
Client (Zupharm) |  |  |  | ⬜ Pending
QA Reviewer |  |  |  | ⬜ Pending

## 🐛 Defect Report
DEFECT REPORT — Zupharm Manufacturing Page v1.0.0
Page URL: localhost:5173/manufacturing ¦ Reported By: SPRINT Team ¦ Date: 30 May 2026
Total Defects: 04
Defect ID | Section | Defect Title | What is Wrong | How to Reproduce | Expected Behaviour | Actual Behaviour | Status
D-001 | Brochure Download | PDF linked to PNG placeholder | The 'Download Brochure' button links to a .png file instead of an actual PDF brochure | 1. Scroll to Manufacturing Capability Brochure section 2. Click 'Download Brochure' 3. Observe downloaded file | A real PDF (4.2 MB) with plant specs and machinery details should download | A PNG placeholder file downloads — no actual brochure content | Open
D-002 | Footer | Placeholder contact details visible | Footer shows dummy phone (+91 12345 67890) and email (info@zupharm.com) — not real client data | 1. Scroll to bottom of page 2. Check Contact section in footer | Real verified Zupharm contact number, email and address should display | Placeholder/dummy data is shown publicly on the live site | Open
D-003 | Quality Section | Accordion background pattern inconsistency | The 'Innovation Backed by Quality Assurance' section shows different background patterns in different states — dot grid vs wave pattern — depending on which accordion item is open | 1. Scroll to Quality Assurance section 2. Open and close each accordion item 3. Observe background | Background pattern should remain consistent regardless of which item is expanded | Background visually shifts/changes on accordion toggle — looks like a UI glitch | Open
D-004 | FAQ Section | FAQ answers truncate on smaller viewports | When FAQ accordion items expand on narrow screen widths, answer text gets cut off or overflows | 1. Open Chrome DevTools 2. Set viewport to 375px (mobile) 3. Expand any FAQ item | FAQ answer text should wrap cleanly within the accordion container at all screen sizes | Text overflows or is partially hidden on mobile viewport | Open